## Sheet1
Sr No | Page name | Details | Priority | Resource working on it | Status | Issues if any
1 | Utility Master | Existing need to change as per required | 1 | Devang | done
2 | mstzone |  | 2 | Devang | done
3 | mstregion |  | 3 | Devang | done
4 | mstdivision |  | 4 | Devang | done
5 | mstsubstation |  | 5 | Devang | done
6 | communicationdetail |  | 1 | Aniket
7 | communicationdetail |  | 1 | Aniket
8 | module Master | Table Name :- mstmodule | 1 | Aniket
9 | menu | Table Name :- mstmenu | 2 | Aniket
10 | Role | Table Name :-mstrole | 3 | Rajneesh | done
11 | Employee | Table Name :-mstemployee | 4 | Rajneesh | done
12 | User | Table Name : Mstuser | 5 | Rajneesh | done
13 | Role Menu Access | Table Name : mstrolemenuaccess | 6 | Rajneesh | done | datatable all record update not working need to rectify
14 | Meter model | Table Name : meter module | 1 | Rajneesh | done
15 | Group Meter |  |  | Rajneesh | done | change model
16 | prmglobal |  |  |  | done
17 | Role Data Access | New pages
18 | Repoter Manual Generation | Page http://localhost/EToolsViewer/ReportManually/Create Table Name : - manualreports |  | Devang | done | Kindly take pages and api from standard 1
19 | WebReportController |  |  | Rajneesh |  | Kindly take pages and api from Unilink Application
20 | Instancedata Api | GetAllInstanceData It is post method with MeterIdList modeil |  |  | done | Kindly check RRVUNL application
21 | DCSG | 3 pages
22 | Standard Alarm |  |  | Devang | done
23 | Real Time Alarm |  |  | Devang | done
24 | ActionType |  |  | Devang | done
25 | MeterType |  |  | Devang | done